## Project Plan
HIDE THESE COLUMNS before printing or sharing with client - DO NOT DELETE
Cigna Implementation Project Plan
Northwest Independent School District | [5 empty] | 2022 Holidays | 2022-05-30
Account Number:3343629 | [6 empty] | 2022-07-04
Effective Date: 09/01/2025 | [6 empty] | 2022-09-05
Revision Date: 07/18/2025 | [6 empty] | 2022-11-24
| Responsibility | [5 empty] | 2022-11-25
Task | Cigna | Northwest ISD | Target Completion Date | Actual Completion Date | Comments |  | 2022-12-26
Administrative Documents and Summaries | [6 empty] | 2022-12-31
Notification of Sale |  | X | 2025-07-10 | 2025-07-10 |  | 2023 Holidays | 2023-01-01
Provide updated Administrative Summary/Structure for review/approval | X |  | 2025-07-14 | 2025-07-14 |  |  | 2023-01-16
Provide Benefit Summaries for review and approval | X |  | 2025-07-16 | 2025-07-18 |  |  | 2022-05-29
Cigna receives approval of proposed employer benefit summaries, summary of benefits and coverage, administrative summary and structure |  | X | 2025-07-25 |  |  |  | 2022-07-04
Open Enrollment | [6 empty] | 2023-09-04
Pre-enrollment line updated with approved summaries for 09/01/2025 | X |  | 2025-08-01 |  |  |  | 2023-11-23
Open enrollment |  | X | 2025-08-15 |  |  |  | 2023-11-24
Eligibility & ID Cards | [6 empty] | 2023-12-25
Account struture in production | X |  | 2025-08-25
Open enrollment file with 2025 changes sent to Cigna |  | X | 2025-08-26
Open enrollment file for 2025 changes updated in Cigna system | X |  | 2025-09-02
DIGITAL ID CARDS
DIGITAL: ID cards released for imaging | X |  | 2025-09-03
DIGITAL ID CARDS available on MyCigna | X |  | 2025-09-08
Billing
First Plan Year 2025 Invoice Prints |  | X | 2025-08-25
System Readiness*
Call system updated with benefit changes | X |  | 2025-09-01
Dental claims released | X |  | 2025-09-01
Summary Plan Documents (SPD)
Cigna provides SPD drafts for review and approval | X |  | 2025-10-06
Approval on SPD provided to Cigna |  | X | 2025-10-27
The dates included in this Implementation Calendar are subject to change. If a change is necessary, Cigna will work with you to reach a new agreement that reflects the changes in circumstances.
The term "Cigna" refers to the various entities which will provide the coverage and/or services described, including, but not limited to, Connecticut General Life Insurance Company, Cigna HealthCare, Cigna Dental, Intracorp, and Cigna Behavioral Care.
Formulas:
Target Completion Date = WORKDAY([Actual Completion Date, row above],5,J6:J21)
Target Completion Date = WORKDAY([Target Completion Date, row above],1,J6:J21)

## Optional Tasks
(NOTE: This worksheet page is included for internal purposes only and should be removed prior to distributing a draft/proposed implementation Project Plan to your Sales Partners and the Client).
OPTIONAL TASKS
Business Day Timing and dependent upon completion date of task # Noted | Task # | Task | Responsible
HSA Tasks - NEW HSA Product adds ONLY (does not apply to transitions)
10 days from CIS | 41 | Conduct HSA Banking Call (Discuss Process and Client funding options) (Note: this is a different/separate banking call from the Medical funding banking call). | Cigna, Client, Broker/Consultant
5 days from #41 | 42 | Client provides decisions from HSA Banking Call | Client
5 days from #42 | 44 | Conduct HSA Technical Call (Discuss Funding file layout, Transmission Methods, Timing, etc.) provide funding agreement to client | Cigna, Client, Broker/Consultant | Wording updated 3/16/2016
3 days from #44 | 45 | Client/vendor provides completed EDT Form(s) indicating Funding File Transmission method | Client/Vendor
10 days from #14 though task 42 needs to be completed | 46 | Client receives HSA Bank Employer Portal Welcome Package | Cigna/Client | for New Business the Client ID must be received from the structure analyst.
10 days from #45 | 47 | Client receives the EDT technical welcome package with file upload instructions | Cigna/Client
TBD | 48 | File transfer testing / Exchange/validate successful test funding files (10-30 days) | Client/Vendor
3 days from #23 | 49 | Cigna sends eligibility to HSA Bank | Cigna
3 days from #49 | 50 | Load eligibility file, invoke Customer Identification Process (CIP), and open bank accounts. | HSA Bank
2 days from #50 | 52 | Debit Cards and Welcome Kits generated (Debit cards are mailed in approximately 14 days) | HSA Bank
effective date or after | 54 | Submit first Funding File | Client
1-5 days after 54 | 55 | Funds loaded | Cigna
External PBM
15 days after CIS | 59 | Obtain Umbrella ID | Cigna/PBM
20 days before effective date | 60 | Confirm integration process setup and ready | Cigna/PBM
FSA Tasks
10 days from CIS | 61A | Banking call for FSA, if the account is fully insured
5 days from #61A | 61B | Client provides decisions from FSA Banking Call | Client
5 days from #61B | 61C | Conduct FSA Technical Call (Discuss Funding file layout, Transmission Methods, Timing, etc.) | Cigna, Client, Broker/Consultant
5 days from 22 | 61D | Funds loaded with Imprest Calculation Amount | Cigna
coordinate dates with medical eligibility files | 61 | Send FSA enrollment/eligibility test file #1 to Cigna | Client/Vendor
coordinate dates with medical eligibility files | 62 | Process FSA enrollment/eligibility test file #1 and provide results | Cigna
coordinate dates with medical eligibility files | 63 | Send FSA contributions test files #1 to Cigna | Client/Vendor
coordinate dates with medical eligibility files | 64 | Process FSA contributions test file #1 and provide results | Cigna
coordinate dates with medical eligibility files | 65 | Send FSA eligibility production file to Cigna | Client/Vendor
coordinate dates with medical eligibility files | 66 | Process FSA eligibility files and deliver error report and provide FSA census counts | Cigna
3-5 business from FSA fund ready- work with Coonsumerism Account Specialist for timing (Note, this only applies when client select debit) | 66A | FSA Debit cards in the mail | Cigna
HRA Tasks
10 days from CIS | 67 | Discuss HRA Administrative documents, contribution amounts, and provisions (HRA Takeover Process, if the Client had HRA with a Prior Carrier); Automated File Specs) | Cigna, Client, Broker/Consultant
10 days from CIS | 68 | Banking Call for HRA accounts, if the account is fully insured.
Eligibility
1 day after Open Enrollment | 69 | SES Submitted | Client
2-5 days after #69 | 70 | SES Processed - File is processed within 2 days - 3 additional days should be built in to accomodate any fallout | Cigna
0 days after #70 | 71 | Eligibility Loaded | Cigna
Clinical / Additional Non-Standard product check for readiness task
coordinate with Clinical IM | 72 | Clinical -- confirm IPHT, CSN, EAP systems (i.e. - ICMS, OLAM) are updated if those products are sold. | Cigna
Note: Under Review - CMT |  | Cigna-HealthSpring Rx (PDP) (EGWP – Employer Group Waiver Provision)
discuss at CIS Meeting | 73 | Review Cigna -HealthSpring Rx (PDP) Employer Guidelines with Client | Cigna
| 74 | Deliver Evidence of Coverage (EOC) proofs to Client for benefit validation (Client must sign off 30 days prior to the effective date for new ERPDP plans and 45 days prior for Renewals). | Cigna
10 Days from Ben sum approval | 75 | Deliver Cigna -HealthSpring Rx (PDP) Contract to Client for signature. | Cigna
prior to client effective date | 76 | Obtain signed Cigna -HealthSpring Rx (PDP) Contract from Client (must be signed prior to effective date). | Client
Cigna Easy Choice Tool
10 days from Ben Sum Approval and/or Client OE date | 77 | Cigna Easy Choice Tool Set Up Complete | Cigna
Client Specific Network(s) CSN
10 days from structure in prod | 78 | Approved Client Specific Network (CSN) Implementation Complete | Cigna
Dedicated 800# set-up
4 - 6 Week lead time for set-up. Discuss during Strategy Call | 79 | Request submitted for client Specific Toll-Free # | Sales/AM
5 business days from Strategy Ca | 80 | Complete Client Information Form | Sales/AM
15 business days from #80 | 81 | Designed Call Flow created and approved | AM/Client
10 business days from # 81 | 82 | Confirm customization of mycigna.com & mobile app | Sales/AM
5 days from #14 | 83 | ID card customization with dedicated 800# | IM
Cigna Rx Medicare (PDP) and Cigna Medicare Advantage Prescription Drug Plan (MAPD)
discuss at CIS Meeting | 84 | Review Cigna Medicare Administrative Guidelines with Client (task should coincide with the Client Interface Session). | MCAM
10 business days after CIS | 85 | Deliver Cigna Medicare Pre-Enrollment communications to Client for review (Typically 10 days after database is loaded and we have approved benefit configurations and Rx grids) | Medicare Communication Specialist
4 business days after # 85 | 86 | Obtain sign-off on Cigna Medicare Pre-Enrollment communications (Mail date must meet CMS timing requirements based on whether passive or open enrollment) | MCAM/Medicare Communication Specialist
6 business days after #86 | 87 | Obtain mailing list from client | MCAM/Medicare Communication Specialist
1 business day after task #87 | 88 | Deliver Evidence of Coverage (EOC) proofs to Client for benefit validation | Medicare Communication Specialist
Partner with the MCAM on the date. As long as it is 30 days before the effective date | 89 | Obtain sign-off on Evidence of Coverage (EOC) proofs (Client must sign off at least 30 days prior to the effective date for new plans. EOCs are automatically mailed within 10 days of the member being accepted by CMS into the Cigna Medicare plan | MCAM/IM/Medicare Communication Specialist
Any date as long as it is at least 2-3 weeks before the effective date | 90 | Deliver Mock ID card template to Client for review | MCAM/IM
10 business days after #90 | 91 | Obtain sign-off on Cigna Medicare ID cards. ID Cards are automatically mailed within 10 days of the member being accepted by CMS into the Cigna Medicare plan. | MCAM/IM
Any date as long as it is 30 days before the effective date | 92 | Deliver Cigna Medicare Contract to Client for signature | MCAM/IM
10 business days from #92 | 93 | Obtain signed Cigna Medicare Contract from Client | MCAM/IM